## Meta (hidden)
Assigned to | priority level | status
Sonia | high | on hold
Neal | medium | ready
Alex | low | in progress
Unassigned |  | testing
All |  | completed

## Backlog
Key | Item | Feature | Bug | Assigned to | Priority | Effort | Status | Description
1 | Gather data | TRUE | 0 | All | high | 3 | ready | Look up and compare various public sources of data. Should relate to hospitalization and insurance plans
2 | Upload data | TRUE | 0 | All | medium | 0.5 | on hold | After finding data, upload to shared git repo into appropriate folder
3 | Shiny investigation | TRUE | 0 | Alex | medium | 3 | ready | Begin researching possibilities with R-shiny. Document top uses with links, code, and images
4 | Shiny template | TRUE |  | Alex | low | 4 | on hold | Make a shiny app template that may fit our use case for the project
5 | Background Research | TRUE | 0 | Unassigned | medium | 4 | ready | Do additional research to gain background and insight into health insurance status quo
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25

## Sprint 1
Key | Item | Feature | Bug | Assigned to | Priority | Effort | Status | Description
1 | Gather data | TRUE |  | All | high | 3 | ready | Look up and compare various public sources of data. Should relate to hospitalization and insurance plans
2 | Upload data | TRUE |  | All | medium | 0.5 | on hold | After finding data, upload to shared git repo into appropriate folder
3 | Shiny investigation | TRUE |  | Alex | medium | 3 | ready | Begin researching possibilities with R-shiny. Document top uses with links, code, and images
5 | Background Research | TRUE |  | Unassigned | medium | 4 | ready | Do additional research to gain background and insight into health insurance status quo